## Instructions
CMMS Implementation Checklist
Phase by phase, from signed contract to a system people actually use
How to use this template
1. Work the Checklist sheet top to bottom. The phases are ordered by dependency, not by convenience.
2. The Gate column is what must be true before the next phase starts. Starting a phase before its gate is met is the most common cause of a late go-live.
3. Assign a named Owner to every line. "The project team" is not an owner.
4. Durations are deliberately absent. They scale with asset count, site count and data quality, and any number printed here would be wrong for most readers. Size them yourself once scope is known.
5. The asset register build is almost always the longest task and the most underestimated. Treat a slip there as a schedule problem, not a data problem.
6. Identify the person who will own the system AFTER go-live during phase 1, not during hypercare. If that role is unfilled at go-live, the implementation decays regardless of how well it was run.
7. Use the Go-Live Readiness sheet as a formal gate. Every line is a yes, or a written and dated accepted exception.
8. Track exceptions rather than hiding them. A known, accepted gap is manageable. An unrecorded one surfaces in week three of hypercare.
Template from MAbbaz.com ¦ enterprise integration and implementation guidance ¦ mabbaz.com

## Checklist
CMMS Implementation Checklist
Status values: Not started / In progress / Done / Exception
Phase | Task | Owner | Gate before next phase | Status | Notes
1 Mobilisation | Name sponsor, project manager, process owner and post-go-live system owner |  | All four roles named and accepted in writing | Not started
1 Mobilisation | Agree governance cadence and escalation path |  |  | Not started
2 Scope and process | Document the current maintenance process before configuring anything |  | Process documented and signed off | Not started
2 Scope and process | Define work types, priorities and SLA rules |  |  | Not started
3 Asset register | Survey sites and capture asset data |  | Register complete, validated and frozen for load | Not started
3 Asset register | Agree hierarchy levels and naming standard |  |  | Not started
3 Asset register | Assign criticality |  |  | Not started
3 Asset register | Data quality gate: no orphans, no duplicates, no blank required fields |  |  | Not started
4 PM library | Build job plans and task lists |  | PM library reviewed by a technician who will use it | Not started
4 PM library | Set frequencies and triggers |  |  | Not started
5 Stores | Build item master and link parts to assets |  | Item master deduplicated | Not started
6 Security | Define roles and permissions |  | Each role tested by a real user of that role | Not started
7 Integration | Build and test each interface |  | Every interface passes a round-trip test | Not started
8 Migration | Decide what NOT to migrate |  | Migration signed off against agreed scope | Not started
8 Migration | Load and reconcile |  |  | Not started
9 Testing | Configuration freeze |  | UAT passed by actual technicians, not proxies | Not started
9 Testing | Run UAT with real technicians on real jobs |  |  | Not started
10 Training | Train by role, not one generic session |  | Every role trained and competence checked | Not started
11 Go-live | Execute the chosen go-live approach |  | Go-Live Readiness sheet fully green | Not started
12 Hypercare | Daily triage of issues with a named responder |  | Issue rate falling for two consecutive weeks | Not started
13 Stabilisation | Review adoption and data quality at 30, 60 and 90 days |  | Owner has a standing improvement backlog | Not started
Template from MAbbaz.com ¦ enterprise integration and implementation guidance ¦ mabbaz.com

## Go-Live Readiness
Go-Live Readiness Gate
Every line is Yes, or a written and accepted exception. No verbal exceptions.
Readiness check | Yes / No | Owner | Exception reference
Asset register loaded, reconciled and signed off
PM schedule generating work orders correctly for the target month
Every user role tested by a real user of that role
Mobile app tested on the actual devices, in an actual dead zone
Interfaces passing round-trip tests in production configuration
Training delivered to every role, with competence checked
Support path published and the week-one responder named
Rollback position understood and agreed
Post-go-live system owner in post and trained
Reporting pack producing correct numbers on migrated data
Template from MAbbaz.com ¦ enterprise integration and implementation guidance ¦ mabbaz.com